## Sheet1
CAPITAL PROJECTS DATABASE
Project Number | Approval Date | Project / Vendor(s) | Service by Contractor | Purchase Order(s) Created | Sub Purchase Order Amount | Project Estimate | Total Difference from Project Estimate | Change Order(s) Total | New Estimated Total with Change Orders | 23-24 Total Expenditures | 24-25 Total Expenditures | Estimated Remaining | Notes
1703 | 2024-04-23 | Chiller Replacement/Upgrade |  |  |  | 827925
|  | OMNIA Racine #3341 |  |  |  | 0 | 616891.92
|  | Wide Hollow Chiller Upgrade | Trane- Chiller | Yes | 101345.04 | 0
Wide Hollow Install
|  | Cottonwood Chiller Upgrade | Trane- Chiller | Yes | 109688.04
|  | Cottonwood Install |  |  |  | 0
1704 |  | Boiler Replacement/Upgrade |  |  |  | 551950
0
0
0
1705 |  | Roof Repair/Replacement Upgrade |  |  |  | 2050812
0
0
1706 |  | Piping Repairs/Upgrade |  |  |  | 685000
0
0
0
1707 |  | Auditorium Storage, Seating ADA Upgrade |  |  |  | 372400
0
0
0
1708 | 2023-09-12 | Gym Bleacher Upgrade |  |  |  | 139500
|  | KCDA Contract 374 |  |  |  |  | -16815.89
|  | Nor Pac Seating | Nor Pac Seating- Bleachers | Yes | 156315.89 | [7 empty] | Estimated Install Date- Summer 2024
1709 |  | Single Use Restroom Project |  |  |  | 1226260
0
0
0
1710 |  | Property Acquisition |  |  |  | 2800000
0
0
0
1712 | 2024-01-23 | MTV Well Upgrade |  |  |  | 644119 | [6 empty] | Start date set for June 12th, earlier if possible for mobilization
|  | RFP- Knobel's Electric | Mt View Well Work | Yes | 617371.2 | 0 | 26747.8 | [5 empty] | Estimated August 23rd completion date
0
1713 |  | Parking Lot Expansion Project |  |  |  | 665000
0
0
0
1714 | 2023-10-24 | Field, Track, Bleachers, Press Box Project |  |  |  | 3556939
|  | OMNIA Contract R220501 |  |  |  |  | 698719
|  | Turf, E-Layer, Endzone, Logo | Coast to Coast- Field | Yes | 641520 |  |  |  |  | 314800 |  | 3242139 | Estimated Start Date- May 27th, 2024
|  | Track, D-Zones, Exchange Zone | Coast to Coast- Track | Yes | 417800 | 0 | [6 empty] | Estimated Completion Date- Aug 15th, 2024
|  | Shot Put Area | Coast to Coast- Shot Put | Yes | 42350
|  | Base Work and Drainage | Coast to Coast- Base work | Yes | 1128750
|  | Bleachers/Fencing | Coast to Coast- ADA | Yes | 417800
|  | Bernardo Wills Consultant | Design West Work | Yes | 210000 | 0
COLUMN TOTALS |  |  |  |  | 3842940.17 | 13519905 | 1325542.83
[5 empty] | Actual Total | Budgeted Amount | Remaining
BUDGET TRACKING TOTAL |  |  |  |  | 3842940.17 | 13519905 | 9676964.83